## RISKS
Project Risk Allowance Calculator
Project Code
Project Name:
Project Mgr:
Risk Number | Risk Title | Project Phase | Risk Treatment | Mitigation Action(s) | Probability | Financial Consequence $ | Risk Cost (Probability x Financial Consequence) $ | Mitigation Cost $ | Risk Allowance $
1 |  |  |  |  | 25% | 10000 | 2500 | 4000 | 4000
2 |  |  |  |  | 40% | 30000 | 12000 | 6000 | 6000
3 |  |  |  |  | 10% | 50000 | 5000 | 8000 | 8000
4 | [6 empty] | 0
5 | [6 empty] | 0
6 | [6 empty] | 0
7 | [6 empty] | 0
8 | [6 empty] | 0
9 | [6 empty] | 0
10 | [6 empty] | 0
11 | [6 empty] | 0
12 | [6 empty] | 0
13 | [6 empty] | 0
14 | [6 empty] | 0
15 | [6 empty] | 0
16 | [6 empty] | 0
17 | [6 empty] | 0
18 | [6 empty] | 0
19 | [6 empty] | 0
20 | [6 empty] | 0
|  |  |  | Total |  | 90000 | 19500 | 18000 | 18000
NOTES
This spreadsheet is designed to assist the calculation of the cost of the risk to the project.
When complete it should be compared to the risk allowance calculated using the risk matrix.
For all major risks an assessment of the probability of occurrence and the financial impact if the risk does occur should be made.
The probability and cost are then multiplied and totalled, producing an overall risk cost for the project.
The cost of mitigating the risks should then be included.
The risk cost and mitigation cost should then be compared.
Where the mitigation cost is lower, this figure should be included.
Where the mitigation cost is higher than the risk cost, but lower than the total financial consequence column, a view of the appropriate cost should be taken and included in the final column.
Where the mitigation cost exceeds the financial cost column, an appropriate assessment should be included.
This is not an exact science and a sensible balanced position should be included, allowing risks to be appropritely managed.
Some of these costs may subsequently be transferred to consultants or contractors for them to manage those risks.

## Lists (hidden)
Likelihood | Priority | Trend | Status | Assumption | Risk Actions | Dep Status | Change Status
3-Highly Likely | 3-High | ▲ Improving | Open | Verified | Avoid | Raised | Requested
2-Possible | 2-Medium | - No Change | Closed | Unverified | Reduce | Communicated | Approved
1-Unlikely | 1-Low | ▼ Deteriorating |  | Rejected | Share | Agreed | Declined
[5 empty] | Retain | Delivered | Applied