## Document Approval
Infrastructure Group - Project Control Registers
DOCUMENT MANAGEMENT & AUTHORISATION
Document Title: | Project Control Registers for Risks, Issues, Change, Key Decisions, Opportunities, lessons Learned & Closed Risks | Version Number: | 1
Document Type: | Templates & Guidance | Document Number: | PMF0002
Business Area/ Function: | Project Management | Application: | For the Management of Infrastructure Projects, within the Infrastructure PM Lifecycle
File Location/link: | \\water.internal\org\02 - Asset Development\Common\Management\Infrastructure PMO
Reviewer/Endorser: | Kevin White | Endorsed by:
Title: | Project Control Manager Lead Business Owner PMF Improvement Project | Date Endorsed:
Reviewer/Endorser: | Nigel Toms | Endorsed by:
Title: | Enterprise Risk Manager | Date Endorsed:
Reviewer/Endorser: | David Blow | Endorsed by:
Title: | Infrastructure Planning Manager Business Owner PMF Improvement Project | Date Endorsed:
Reviewer/Endorser: | Tim Munro | Endorsed by:
Title: | Major Projects Manager Business Owner PMF Improvement Project | Date Endorsed:
Document Owner/ Approver: | Dominic Hollewand | Approved by:
Title: | Manager Infrastructure Program, Sponsor of PMF Improvement Project | Date Approved:

## RISKS
Project Risk Register
Project Code |  | 0
Project Name: |  | 0
Project Objective: |  | 0
Project Mgr: |  | 0
Risk Number | Overall Rating | Probability | Consequence | Risk Title | Project Phase | Risk Cause | Risk Consequence | Risk Treatment | Mitigation Action(s) | Risk Cost $ | Risk Owner | Due Date | Display on PSR
1 | 0
2 | 0
3 | 0
4 | 0
5 | 0
6 | 0
7 | 0
8 | 0
9 | 0
10 | 0
11 | 0
12 | 0
13 | 0
14 | 0
15 | 0
16 | 0
17 | 0
18 | 0
19 | 0
20 | 0

## Issues
Issue Register
Project Code |  | 0
Project Name: |  | 0
Project Objective: |  | 0
Project Mgr: |  | 0
Issue # | Date raised | Raised By | Issue Title | Issue Description | Issue Type | Impact | Issue Priority | Issue Owner | Action(s) | Action Owner | Due Date | Status | Display on PSR | Date Closed
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Change
Change Request Register
Project Code |  | 0
Project Name: |  | 0
Project Objective: |  | 0
Project Mgr: |  | 0
Change # | Contract # | Date Raised | Raised By | Change Title | Change Description | Change Type | Change Impact (select as appropriate) |  |  | Total Cost $ | Status | Other Register Ref(s) | Approval By | Date Approved
[7 empty] | Time | Cost | Scope
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Decisions
Key Decisions Register
Project Code |  | 0
Project Name: |  | 0
Project Objective: |  | 0
Project Mgr: |  | 0
Decision # | Date Raised | Raised By | Decision Title | Decision Required | Approval By | Decision Made | Date Approved | Change Request Required? (Y/N) | Status | Link to Supporting documentation e.g minutes, options paper
D-001
D-002
D-003
D-004
D-005
D-006
D-007
D-008
D-009

## Lists (hidden)
Likelihood | Priority | Trend | Status | Assumption | Risk Actions | Dep Status | Change Status
3-Highly Likely | 3-High | ▲ Improving | Open | Verified | Avoid | Raised | Requested
2-Possible | 2-Medium | - No Change | Closed | Unverified | Reduce | Communicated | Approved
1-Unlikely | 1-Low | ▼ Deteriorating |  | Rejected | Share | Agreed | Declined
[5 empty] | Retain | Delivered | Applied

## Opportunities
Opportunities Register
Project Code |  | 0
Project Name: |  | 0
Project Objective: |  | 0
Project Mgr: |  | 0
Opportunity Number | Opportunity Desctiption |  | Benefit to the Project or Business | Cost to Implement | Time to Implement | Resources to Implement | Actionee | Review/ Completion Date | Status
O-001
O-002
O-003
O-004
O-005
O-006

## Lessons Learned
Lessons Learned Register
Project Code |  | 0
Project Name: |  | 0
Project Objective: |  | 0
Project Mgr: |  | 0
Lesson # | Date Raised | Raised By | Lesson Title | Lesson Type | Project Phase | Project/System Type | Lesson Learned Description | Negative/ Positive | Recommended Improvement Action(s) | Assigned to | Link to Supporting documentation
L-001
L-002
L-003
L-004
L-005
L-006
L-007
L-008
L-009
L-010
|  |  |  | Assumption | Idea | Idea
|  |  |  | Budget Mgmt | Initiation | Initiation
|  |  |  | Change Control | Design | Design
|  |  |  | Communications | Build | Build
|  |  |  | Constraints | Test | Test
|  |  |  | Deliverables | Release | Release
|  |  |  | Governance | Warranty | Warranty
Handover
Integration
People Mgmt
Process
Procurement Mgmt
Quality Mgmt
Risks
Schedule
Scope

## Closed RISKS
CLOSED Risk Register
Project Code |  | 0
Project Name: |  | 0
Project Objective: |  | 0
Project Mgr: |  | 0
Risk # | Overall Rating | Probability | Consequence | Risk Title | Project Phase | Risk Cause | Risk Consequence | Risk Treatment | Mitigation Action(s) | Risk Cost $ | Risk Owner | Due Date | Display on PSR | Date Closed
1 | 0
2 | 0
3 | 0
4 | 0
5 | 0
6 | 0
7 | 0
8 | 0
9 | 0
10 | 0
11 | 0
12 | 0
13 | 0
14 | 0
15 | 0
16 | 0
17 | 0
18 | 0
19 | 0
20 | 0

## Instructions
Project Control Registers - INSTRUCTIONS
Enter the Project Code, Name etc in boxes below - this will populate the same fields in all of the Registers in this workbook.
Project Code
Project Name:
Project Objective:
Project Manager:
Risk Assessment Matrix
PROBABILITY | Very High | Low | Medium | High | Very High | Very High |  |  | Project Stages | Project Status
| High | Low | Medium | High | Very High | Very High |  |  | PLANNING | Open
| Medium | Low | Low | Medium | High | High |  |  | DESIGN | Closed
| Low | Very Low | Low | Medium | Medium | High |  |  | CONSTRUCTION
| Very Low | Very Low | Low | Low | Medium | Medium |  |  | COMMISSIONING
|  | Very Low | Low | Medium | High | Very high |  |  | OPERATION
CONSEQUENCE
Standard Project Risk Assessment Criteria |  |  |  |  | The Risk Assessment Criteria are project specific & should be defined for the project at the first Risk Workshop. Consequence criteria (Cost, Time & Quality) should be defined in the context of the project's budget, timeline/programme & benefits. Probability criteria can be changed, however, the standard range will work for most projects. Criteria can be revised if they are not a good fit for the project.
PROBABILITY CRITERIA |  | CONSEQUENCE CRITERIA
RANKING | PERCENTAGE % | RANKING | RATING | COST |  | DELAY TIME | Quality
|  |  |  | % Project Cost | Cost $K | Weeks
VERY HIGH | > 75 | VERY HIGH | 5 | > 75 | >20 | 10 | Project specific | Quality criteria should be defined
HIGH | 50 - 75 | HIGH | 4 | 50 - 75 | 100 - 200 | 8 |  | based on the impact on the Objective,
MEDIUM | 20 - 50 | MEDIUM | 3 | 25 - 49 | 50 - 99 | 4 |  | Performance or Quality of the Project.
LOW | 5 - 20 | LOW | 2 | 10 - 24 | 10 - 49 | 2 |  | Do not complete this exercise in the
VERY LOW | < 5 | VERY LOW | 1 | <10 | <10 | 1 |  | Risk Workshop
Risk Register
Field Name | Guidance
Risk Number | The number is risk specific and should not be re-used if the risk is closed.
Overall Rating | This will be calcuated automatically given the values entered into the Probability & Consequence cells. See the Risk Asessment Matrix above for the WSL approach to risk rankings.
Probability | Select a rating for the Probability of the risk occuring of either Very High, High, Medium, Low, Very Low, from the drop-down list.
Consequence | Select a rating for the Consequence if the risk occurs of either Very High, High, Medium, Low, Very Low, from the drop-down list.
Risk Title | A short overall description of the risk e.g. "Unknown Archaeology"
Project Phase | The project phase where the risk would imact.
Risk Cause | Describe what causes the risk to occur.
Risk Consequence | Describe the effect of the risk if it were to occur and impact the project. Consider in terms of impact on the project cost, schedule of performance/quality once completed.
Risk Treatment | The agreed response to this risk. Select from drop down list: Transfer - risk and related responsibility for management and the liability is passed on to a third party. Tolerate - level of risk is accepted if impact is low or mitigation not cost-effective. If impact is high, management should be informed. Treat - action(s) will be taken to reduce the probability of occurrence or the impact it it does occur. Terminate - the risk is unacceptable & the associated objective will not be pursued.
Mitigation Action(s) | Describe the mitigation action(s) for the risk. There can be more than one action. Be clear about what the Risk Owner is actually required to do to mitigate the risk. Each mitigation action should have an Owner & Due Date for completion.
Risk Cost | The cost to the pioject if the risk were to materialise. Multiply by the Probability % by the Impact Cost. This will provide an outline estimate only.
Risk Owner | The person best placed to manage the risk. Can be an internal or external party
Due Date | The date that the mitigation action should be completed or the next review/update should have been completed.
Display on PSR | The top 5 rated risks (Very Highs & Highs) should be flagged for inclusion in Infrasturcture project status reporting.
Closed Risk Register (move Closed risks into this register)
Field Name | Guidance
Date Closed | Enter the date the Risk was closed
Issue Register
Field Name | Guidance
Issue Title | A short label for the issue e.g. "Consenting taking longer than anticipated"
Issue Description | A clear, concise statement describing the issue.
IssueType | Choose from drop-down list as appropriate- Design/Technical,Process, Legal, Regulatory,Legal,Stakeholders,Resources, Procurement,Contractor
Impact | Describe the impact on the project objectives/ time/cost
Issue Priority | Choose from drop-down selection - High, Medium or Low depending on the urgency of the issue to be resolved. The impact of the issue should be considered here.
Issue Owner | The person best placed to manage the issue & ultimately accountable for it's resolution. Can be an internal or external party
Action(s) | Describe the action to resolve this issue. There can be more than one action. Each action should have an Owner & Due date. For updates on an action's progress precede the update with the date of the update
Action Owner | Owner of an action to manage this issue. There may be multiple actions
Display on PSR | The top 5 Issues (High Priority) should be flagged for inclusion in the Infrasturcture project status reporting.
Change Control Register - fields to be copied from the Change Request Form
Field Name | Guidance
Contract # | If the change is relating to an element of a Contract there should be a contract number on the CR Form
Change Title | A short label for the Change, from the CR Form
Change Description | A clear, concise statement describing the issue, from the CR Form
Change Type | Select from drop-down list - Technical/Design,Process/Policy, Scope,Legal/Regulatory or Strategic
Change Impact | Select Yes in the boxes for the project mangement areas that are impacted by this change - Time/Cost/Scope or a combination of these
Total Cost | The total cost of implementing this change, from the CR Form
Status | Choose from drop-down selection - Requested,Approved,Declined
Other Register Ref(s) | If there is a new risk/issue/decision/lesson as a result of this change enter the relevant reference number here
Approval By | Enter the Approver's Name, from the CR Form
Key Decisions Register
Field Name | Guidance
Decision Title | A short label for the decision subject matter
Decision Required | Description of the decision required to be made, if logging a decision that has not been made yet
Decision Made | Description of the Decision made by the Approver
CR Required? | Select Yes or No from the drop-down list depending on the need for a Change Request as a result of this decision
Link to Supporting documentation | Enter hyperlink(s) here to supporting documents e.g. minutes, options paper
Opportunities Register
Field Name | Guidance
Opportunity Description | Describe the opportunity - the action that if included in the project would enhance the project objectives/benefits or would deliver other WSL benefit(s)
Benefit to the Project or Business | Describe the benefit of implementing this opportunity, to the project and/or for the wider WSL business
Resources to Implement | Enter an estimate of FTE & resource skill type(s) required to implement this opportunity
Lessons Learned Register
Field Name | Guidance
Lesson Title | A short label for the Lesson subject matter
Lesson Description | Describe what was learned & the circumstances
Lesson Type | Select the area that the Lesson pertains to from drop-down list - People, Process or Tools
Project Phase | Select a PM Lifecycle Phase from the drop-down list - Definition, Feasibility, Design,Execution or Closure
Lesson Type | Select from the drop-down list - Networks Water,Networks Wastewater,Wastewater Treatment,Water Treatment,Labs,Project
Negative/Positive | Select from the drop-down list - Negative or Positive